## Overview
SQLPath — Project Tracker
Cohort-based SQL practice platform · NestJS + Next.js monorepo · last synced against codebase 2026-08-22
How to use this workbook
• Tasks — general backlog for backend/frontend work. Update Status and % Complete as you go.
• Known Issues & Gaps — the specific gaps called out in project docs (migrations, tests, seed data) plus bugs you find.
• Question Bank — tracks progress toward the ~350 planned SQL questions by phase/platform/difficulty.
• Deployment Checklist — readiness items for shipping the Railway monolith deploy.
• Cells shaded yellow are meant to be edited. Dropdowns are provided for Status/Priority columns.
Snapshot
Metric | Value
Total tasks | 11
Tasks done | 6
Tasks in progress | 2
Tasks blocked | 0
Open known issues | 6
Questions seeded | 31
Questions planned | 350
Question bank completion | 8.857%
Deployment items done | 0
Deployment items total | 14

## Tasks
Task / Feature Tracker
Backend + frontend backlog
ID | Area | Task | Description | Status | Priority | Owner | Notes
1 | Backend | Write initial SQL migrations | Create migration files for users, questions, solves, cohorts, score_ledger, daily_activity, trust_events, anti_gaming_flags, verification_queue tables | Not Started | High |  | synchronize is off; schema must exist before app/seed run. Still no migrations/ folder as of latest review.
2 | Backend | Expand question bank seed data | Grow seed/seed.ts toward the ~350 planned questions | In Progress | Medium |  | 31/350 seeded (up from ~30), covering phases 1-6 only; phases 7-8 (CTEs & Recursion, Production Case Studies) have none yet
3 | Backend | Add automated test suite | No tests exist yet; start with auth, solves scoring, and verification tier routing | Not Started | Medium |  | still no test/ directory in backend
4 | Frontend | Add shared API response types | api.ts responses are largely `any`; define shared types with backend DTOs | In Progress | Low |  | auth/profiles calls now have partial typed shapes, but most responses (questions, solves, mentor) are still `any`
5 | DevOps | Verify Railway monolith deploy | Confirm Dockerfile + docker-entrypoint.js behave correctly end-to-end on Railway | Not Started | High |  | see DEPLOY-MONOLITH.md; no changes detected to Dockerfile/entrypoint since last review
6 | Backend | Add boot-time env var validation | Fail fast with a clear error if DATABASE_URL/JWT_SECRET are missing or JWT_SECRET is too short | Done | Medium |  | src/config/env.validation.ts added
7 | Backend | Build multi-platform profile stats | New profiles module: link Codeforces/GeeksforGeeks/HackerRank usernames and fetch stats per platform, alongside existing LeetCode verification | Done | Medium |  | profiles.controller.ts / profiles.service.ts + frontend api.ts wiring
8 | Frontend | Build Activity page | Student-facing feed combining solves, verifications, and per-platform stats | Done | Medium |  | src/app/activity/page.tsx
9 | Frontend | Build Progress page | Phase-by-phase roadmap detail view (1. Basics & Filtering → 8. Production Case Studies) | Done | Medium |  | src/app/progress/page.tsx
10 | Frontend | UI/UX overhaul | Design-token based theming, framer-motion animations, Confetti/CountUp/Loader/Skeleton components, new StudentLayout shell, toast notifications | Done | Medium |  | package.json now includes framer-motion; several new components under src/components
11 | Backend | Simplify role model | Collapsed mentor/admin distinction to a single ADMIN role (Role enum now STUDENT ¦ ADMIN only) | Done | Low |  | PROJECT.md docs still describe a separate 'mentor' role — docs are stale, recommend updating

## Known Issues & Gaps
Known Issues & Gaps
Seeded from current project docs — add bugs as you find them
ID | Type | Area | Description | Impact | Status | Date Logged | Notes
1 | Gap | Backend/DB | No SQL migration files present | Schema must be manually applied to Postgres before app or seed script will run | Open |  | TypeORM synchronize is intentionally off; still true as of latest review
2 | Gap | Backend | Question bank incomplete | 31 of ~350 planned questions seeded; phases 7-8 have zero questions | Open |  | seed/seed.ts covers phases 1-6 only (10/5/5/5/3/3)
3 | Gap | Backend | No automated test suite | No safety net for regressions in scoring/verification/anti-gaming logic | Open
4 | Gap | Frontend | No shared type contract with backend | Most API response types are still `any` in api.ts | Open |  | Improved slightly — profiles/auth endpoints now have partial typed shapes
5 | Tech Debt | Docs | PROJECT.md files are out of date vs. code | Backend/frontend PROJECT.md still describe a 3-role model (student/mentor/admin) and the older phase names/question counts; code has since simplified to student/admin and added profiles, activity, and progress features | Open |  | Recommend refreshing PROJECT.md alongside future feature work
6 | Gap | Backend | GeeksforGeeks has no seeded questions | Platform enum includes GEEKSFORGEEKS for the question bank, but seed.ts currently seeds 0 questions on it (only used today for profile-stats linking) | Open

## Question Bank
Question Bank Progress
Target: ~350 questions across 8 phases (Basics & Filtering → Production Case Studies)
Phase | Platform(s) | Planned Qs | Seeded Qs | % Complete | Notes
1. Basics & Filtering | LeetCode, HackerRank, SQLZoo | 40 | 10 | 25% | SELECT, WHERE, LIKE, IN/BETWEEN, ORDER BY, LIMIT
2. String, Date & CASE | LeetCode, HackerRank | 40 | 5 | 12.5% | CONCAT, SUBSTRING, DATE_ADD, CASE WHEN, COALESCE
3. Aggregation & Grouping | LeetCode, DataLemur | 45 | 5 | 11.11% | COUNT, SUM/AVG, GROUP BY, HAVING, DISTINCT
4. Joins & Relational Data | LeetCode, StrataScratch | 50 | 5 | 10% | INNER/LEFT/RIGHT/SELF/CROSS JOIN
5. Subqueries & Set Operations | LeetCode, HackerRank | 45 | 3 | 6.667% | Subqueries, EXISTS, UNION/UNION ALL
6. Window Functions | LeetCode, StrataScratch | 40 | 3 | 7.5% | ROW_NUMBER, RANK, LEAD/LAG, OVER (PARTITION BY)
7. CTEs & Recursion | DataLemur, GeeksforGeeks | 45 | 0 | 0% | Not yet seeded — WITH clauses, recursive CTEs, hierarchies
8. Production Case Studies | StrataScratch, DataLemur | 45 | 0 | 0% | Not yet seeded — retention/funnel/revenue analysis, optimization
Total |  | 350 | 31 | 8.857%

## Deployment Checklist
Deployment Checklist
Railway monolith deploy — see DEPLOY-MONOLITH.md
Item | Category | Details | Status | Notes
DATABASE_URL set | Env Vars | Postgres/Supabase connection string | Not Started
JWT_SECRET / JWT_EXPIRES_IN set | Env Vars |  | Not Started
SUPABASE_URL / SUPABASE_SERVICE_KEY set | Env Vars |  | Not Started
SCREENSHOT_BUCKET configured | Env Vars | Supabase Storage bucket for solve screenshots | Not Started
FRONTEND_URL set for CORS | Env Vars |  | Not Started
BACKEND_INTERNAL_URL / BACKEND_INTERNAL_PORT set | Env Vars | Used by docker-entrypoint.js and next.config.ts rewrite | Not Started
SQL schema applied to target DB | Database | synchronize is off — migrations must run first | Not Started
Seed script run (if demo data desired) | Database | npm run seed | Not Started
Docker image builds locally | Build | npm run docker:build | Not Started
Docker image runs locally | Build | npm run docker:run | Not Started
railway.json (root) used, not per-app ones | Deploy Config | Don't mix root and per-service railway.json files | Not Started
Health check / restart-on-crash verified | Deploy Config | Entrypoint exits if either process dies | Not Started
Production smoke test: login + submit a solve | Verification |  | Not Started
Production smoke test: mentor/admin queue + risk dashboard | Verification |  | Not Started | Role model simplified to STUDENT/ADMIN — 'mentor' is now just the admin-facing UI